## Grouped List
Ref # | Name | PM | Pln Comp | Proj Comp | %Comp | Status | Priority | Progress | Has Nts | Has Docs | Issues | Is Approval
Account Manager: Braedon Armstrong (47)
6351 | WOAWS 6351 Alta Woodlake Square Copilot Splash + Website + Mobile | Ian | 2/21/13 | 2/22/13 | 89.9 | Current | Normal | At Risk | true | true | true | Approval Not Required
6451 | WOAHI 6451 Alta Heights Copilot Splash + Website + Mobile | Patricia | 4/4/13 | 4/4/13 | 18.6 | Current | Normal | At Risk | true | true | true | Approval Not Required | waiting client feedback on HP
1911 | PW 1911 Property West Corp + Property Websites | Ian | 1/31/13 | 2/13/13 | 97.9 | Current | Normal | At Risk | true | true | true | Approval Not Required
1652 | ECRRG 1652 Regency Ridgegate Identity and Signage | Ian | 2/7/13 | 2/12/13 | 96.5 | Current | Normal | In Trouble | true | true | true | Approval Not Required
2450 | MSTEN 2450 Pine Street Flats Phase 1 | Ian | 10/18/12 | 2/12/13 | 99.6 | Current | Normal | On Target | true | true | false | Approval Not Required
2403 | SRPRV 2403 The Promenade Brochure & Stationery Design | Ian | 2/14/13 | 2/26/13 | 77.1 | Current | Normal | On Target | true | true | false | Approval Not Required
4750 | EC 4750 Echelon Corporate Refresh & New Residential Corporate Site | Ian | 3/25/13 | 3/22/13 | 84.8 | Current | Normal | On Target | true | true | false | Approval Not Required
5806 | BSWEP 5806 Woodland Estates | COMPLETE | 2/22/13 | 2/18/13 | 84.7 | Current | Normal | At Risk | true | true | false | Approval Not Required | ??
5809 | KC 5809 Klingbeil Property CoPilot + Mobile Websites | Ian | 4/12/13 | 4/11/13 | 79.5 | Current | Normal | On Target | true | true | false | Approval Not Required
6350 | WOAAS 6350 Alta Alameda Station Copilot Splash + Website + Mobile | Patricia | 3/18/13 | 3/18/13 | 77.9 | Current | Normal | On Target | true | true | false | Approval Not Required | Internal review HP pages
9303 | FCAPL 9303 First Communities - Ashford Place | Ian | 10/12/12 | 2/12/13 | 95.9 | Current | Normal | In Trouble | true | true | false | Approval Not Required
9304 | FCBRC 9304 First Communities Briar Creek | Ian | 10/12/12 | 2/12/13 | 95.7 | Current | Normal | In Trouble | true | true | false | Approval Not Required
9305 | FCAVI 9305 First Communities - Ashford Villas | Ian | 10/12/12 | 2/12/13 | 96.4 | Current | Normal | In Trouble | true | true | false | Approval Not Required
9306 | FCSIP 9306 First Communities Sierra Place | Ian | 10/15/12 | 2/12/13 | 95.7 | Current | Normal | In Trouble | true | true | false | Approval Not Required
9504 | EC 9504 Echelon - Parker Hilltop - Rebranding | Ian | 1/29/13 | 4/25/13 | 65.7 | Current | Normal | In Trouble | true | true | true | Approval Not Required
9800 | FCHAD 9800 First Communities - Hampton Downs - Copilot, Resident Portal, Mobile, iPad | Allyah | 2/27/13 | 2/14/13 | 94.4 | Current | Normal | On Target | true | true | true | Approval Not Required
9801 | FCSIR 9801 First Communities - Sienna Ridge | Allyah | 2/12/13 | 7/23/13 | 52.5 | Current | Normal | At Risk | true | true | true | Approval Not Required
10002 | JMVEL 10002 JMG - Villages of Eastlake ¦ Brochure ¦ Letterhead | Ian | 2/5/13 | 2/12/13 | 95.7 | Current | Normal | In Trouble | true | true | false | Approval Not Required
10203 | SRCYP 10203 Sares Regis - Canyon Park brochure | Ian | 1/2/13 | 2/13/13 | 92.6 | Current | Normal | In Trouble | true | false | false | Approval Not Required
11451 | PWBHH 11451 Property West - Hawaii House | Patricia | 3/18/15 | 3/17/15 | 1.2 | Current | Normal | On Target | true | false | false | Approval Not Required | on hold
12800 | FCACE 12800 First Communities - Amber Chase - CMS - Resident Portal- Mobile - iPad - SEO | Ian | 12/13/12 | 2/13/13 | 72.6 | Current | Normal | In Trouble | true | true | true | Approval Not Required
13150 | 13150 Whiteco - 5250 Houston - CoPilot - Mobile - Splash Page - SEO | Patricia | 3/28/13 | 3/22/13 | 72.8 | Current | Normal | On Target | true | true | false | Approval Not Required | HP approved
13350 | ECPKH_13350_Parker Hilltop_Copilot | Patricia | 3/25/13 | 3/28/13 | 62.6 | Current | Normal | On Target | true | false | false | Approval Not Required | waiting on cleint feedback on HP
14004 | FCALA 14004 First Communities - Asford Lake Apartments - CoPilot, Resident Portal, Mobile, Ipad | Ian |  | 2/20/13 | 73.5 | Current | Normal | In Trouble | true | true | false | Approval Not Required
14003 | SRRIO 14003 Sares Regis - The Lofts at Rio Salado - VIP Cards | Ian | 11/30/12 | 2/12/13 | 82.9 | Current | Normal | In Trouble | true | false | false | Approval Not Required
14102 | 14102 Wood Partners - Creek Side Brochure | Ian | 11/30/12 | 2/22/13 | 23.2 | Current | Normal | In Trouble | true | false | false | Approval Not Required
14205 | First Communities - 14205 - Ivy Hall Apartments - Copilot - Mobile - iPad - Resident Portal - Seo | Ian | 2/18/13 | 2/28/13 | 72.8 | Current | Normal | At Risk | true | true | true | Approval Not Required
14351 | Stonemark 14351 - Radico - Ashford Gardens - CMS - Mobile | Ian | 1/18/13 | 2/15/13 | 41.3 | Current | Urgent | In Trouble | true | false | false | Approval Not Required
15000 | BR 15000 Bonaventure - 14 Properties - Website + Mobile + iPad | Allyah | 3/22/13 | 3/22/13 | 58.2 | Current | Normal | On Target | true | true | true | Approval Not Required
14550 | WOALA 14550 - Alta Warner Website + Mobile + SEO | Allyah | 2/28/13 | 2/28/13 | 57.1 | Current | Normal | On Target | true | true | false | Approval Not Required
14659 | FCWRU 14659 First Communities - Walden Run - CoPilot - Mobile - iPad - E-Brochure - SEO | Ian | 2/25/13 | 3/6/13 | 55.3 | Current | Normal | At Risk | true | true | false | Approval Not Required
15702 | BSPSF 15702 - Pine Street Flats - Floor Plan Browser | Patricia | 4/3/13 | 4/22/13 | 0.2 | Current | Normal | At Risk | true | false | false | Approval Not Required | Transfer
15703 | FCEWV 15703 - First Communities - Edgewater Vista - CMS Website + Resident Portal | Patricia | 1/29/13 | 2/21/13 | 11 | Current | Normal | In Trouble | true | false | false | Approval Not Required | ?
15700 | AS 15700 - Asher Investments - Responsive Design + SEO | Patricia | 4/17/13 | 4/17/13 | 0.2 | Current | Normal | On Target | true | true | false | Approval Not Required | May
15855 | GR 15855 - Greystone - 6 New Properties - CMS Set Up | COMPLETE | 2/14/13 | 2/19/13 | 79.8 | Current | Normal | At Risk | true | false | false | Approval Not Required | ?
16150 | CR 16150 - Compass Rock - Riverton Square - Website + Mobile | Patricia | 4/4/13 | 4/15/13 | 12.3 | Current | Normal | At Risk | true | false | false | Approval Not Required | send ho,me page to client
16550 | FC 16550 First Communities - Century - Century Trinity Estates -CMS - Mobile - SEO | Patricia | 2/26/13 | 2/14/13 | 74.2 | Current | Normal | On Target | true | true | true | Approval Not Required | ? SEO?
16652 | AAVAR 16652 AGI - Vara - Responsive Design Full Website | Patricia | 4/25/13 | 5/3/13 | 1.3 | Current | Normal | At Risk | true | false | false | Approval Not Required
16653 | BM- 16653 Briarcliff Management - Corporate site - - resident portal - online app - ipad - mobile - SEO | Patricia | 4/25/14 | 5/3/14 | 2.3 | Current | Normal | At Risk | true | false | false
16654 | BM- 16654 Briarcliff Management - 2 Properties - resident portal - online app - ipad - mobile - SEO | Patricia | 4/19/13 | 4/18/13 | 4.6 | Current | Normal | On Target | true | true | false | Approval Not Required
16750 | STASM 16750 Radco - Ashford at Geneva | Patricia | 2/28/13 | 2/28/13 | 4.9 | Current | Normal | On Target | true | false | false | Approval Not Required
16950 | WOVario 16950 Wood Partners - Alta Woodlake-Alta Alameda Station Floorplans | Patricia | 3/1/13 | 3/1/13 | 11.8 | Current | Normal | On Target | true | false | false | Approval Not Required
17101 | SRBHR 17101 Sares Regis - The Bluffs At Highlands Ranch - CMS - Mobile | Patricia | 2013-02-12 | 2013-02-25 | 0 | Current | Normal | On Target | true | false | false
Account Manager: Jenny Hill (44)
1552 | GATWY 1552 Gateway Apts & Townhomes Brochure | Patricia | 2/21/13 | 2/12/13 | 62.5 | Current | Normal | At Risk | true | true | false | Approval Not Required
2301 | KFVIN 2301 1600 Vine Brand Identity + Campaign Theme | Patricia | 2/12/13 | 2/12/13 | 94.6 | Current | Normal | On Target | true | true | true | Approval Not Required
5808 | AERPK 5808 AMLI Riverfront Park Signage | Patricia | 2/18/13 | 2/19/13 | 81.7 | Current | Normal | At Risk | true | true | false | Approval Not Required
5901 | WR 5901 Woodmont Sobrato Theme | Allyah | 2/19/13 | 3/4/13 | 97 | Current | Normal | At Risk | true | true | false | Approval Not Required
6955 | MITRI 6955 Trilogy Website Copilot Site, Splash Page, Floorplan Browser | Allyah | 2/8/13 | 2/14/13 | 97.4 | Current | Normal | On Target | true | true | true | Approval Not Required
9702 | LCTAS 9702 LCOR: 121 Tasman, Branding Package | Patricia | 2/8/13 | 2/25/13 | 64.2 | Current | Normal | In Trouble | true | true | false | Approval Not Required
10657 | WA 10657 Wasatch Responsive Design Website | Patricia | 2/19/13 | 2/19/13 | 87.9 | Current | Normal | At Risk | true | true | true | Approval Not Required
12600 | WA 12600 Portal Refresh | Ian | 4/15/13 | 5/16/13 | 52.3 | Current | High | On Target | true | true | false | Approval Not Required
13602 | 13602 LEVIN 1600 Vine Stationery | Patricia | 2/11/13 | 2/13/13 | 65.7 | Current | Normal | In Trouble | true | false | false | Approval Not Required
14051 | CP 14051 Carmel Midtown Square 12 page brochure | Patricia | 2/8/13 | 2/20/13 | 44.5 | Current | Normal | In Trouble | true | false | true | Approval Not Required
14452 | CP 14452 Carmel Midtown Square window graphics | Patricia | 2/1/13 | 2/15/13 | 52.3 | Current | Normal | In Trouble | true | false | false | Approval Not Required
14407 | 21100 Trilogy Dynamic Email | Patricia | 2/11/13 | 2/12/13 | 28.6 | Current | Normal | On Target | true | true | false | Approval Not Required
14752 | RVMOM 14752 Modera Miramar Green Living page | Allyah | 12/27/12 | 2/15/13 | 16.6 | Current | Normal | In Trouble | true | true | false | Approval Not Required
14903 | CPWHI 14903 Carmel: Waterfront at Puuloa Floor plan display | Patricia | 2/1/13 | 2/1/13 | 100 | Current | Normal | On Target | true | true | false | Approval Not Required
15050 | CP 15050 Carmel Midtown Square 3D floor plans | Patricia | 2/21/13 | 2/28/13 | 37.2 | Current | Normal | At Risk | true | true | false | Approval Not Required
15051 | CPERI 15051 Carmel Hacienda Heights Brochure | Patricia | 1/30/13 | 2/12/13 | 70.8 | Current | Normal | In Trouble | true | false | false | Approval Not Required
15057 | CPCHW 15057 Carmel Midtown Square Site Map | Patricia | 2/7/13 | 2/12/13 | 77.1 | Current | Normal | In Trouble | true | true | false | Approval Not Required
15058 | CPCTV 15058 Carmel The Village 11x17 site map | Patricia | 2/12/13 | 2/20/13 | 55 | Current | Normal | At Risk | true | false | false | Approval Not Required
15150 | CPDEN 15150 Carmel Q1 2013 Campaign | Patricia | 3/25/13 | 3/25/13 | 87.9 | Current | Normal | On Target | true | true | false | Approval Not Required
15600 | CPCTV 15600 - Carmel The Village - Video | Patricia | 3/7/13 | 3/13/13 | 19.4 | Current | Normal | At Risk | true | false | false | Approval Not Required
15551 | CPPAC 15551 - Carmel Pacific Ridge - Video | Patricia | 3/6/13 | 3/15/13 | 16.3 | Current | Normal | At Risk | true | false | false | Approval Not Required
15706 | CPWES 15706 Westwood brochure | Patricia | 2/8/13 | 2/12/13 | 94.5 | Current | Normal | In Trouble | true | true | false | Approval Not Required
15704 | 15704 Ramble Brochure | Patricia | 2/21/13 | 2/21/13 | 64.6 | Current | Normal | On Target | true | true | false | Approval Not Required
15851 | CPVA 15851 Bear Valley Temp Brochure + Illustrations | Patricia | 3/1/13 | 2/26/13 | 43.9 | Current | Normal | On Target | true | true | true | Approval Not Required
16100 | CPVUE 16100 Carmel Vue keychain reorder | Patricia | 2/1/13 | 2/7/13 | 100 | Current | Normal | In Trouble | true | true | false | Approval Not Required
16101 | LCTAS 16101 121 Tasman Flyers | Patricia | 2/18/13 | 2/18/13 | 14.8 | Current | Normal | At Risk | true | true | false | Approval Not Required
16103 | WODSM 16103 Alta San Marcos Website + Mobile | Allyah | 2/15/13 | 2/27/13 | 36.6 | Current | Normal | At Risk | true | true | false | Approval Not Required
16200 | LeaseLabs Website - 16200 | Ian | 2/19/13 | 2/26/13 | 24.4 | Current | Normal | At Risk | true | false | false | Approval Not Required
16303 | CPCTV 16303 Carmel The Village stickers | Patricia | 2/5/13 | 2/14/13 | 92.6 | Current | Normal | In Trouble | true | false | false | Approval Not Required
16302 | CPMAD 16302 Carmel: Madrid no glass allowed sign | Patricia | 2/14/13 | 2/12/13 | 92.6 | Current | Normal | On Target | true | false | false | Approval Not Required
16400 | CPSOL 16400 Solstice brochure | Patricia | 2/19/13 | 2/21/13 | 35 | Current | Normal | At Risk | true | false | true | Approval Not Required
16500 | CPWVI 16500 West Village mailer insert | Patricia | 2/11/13 | 2/12/13 | 89.4 | Current | Normal | In Trouble | true | true | false | Approval Not Required
16651 | 16651 -1600 Vine Website Fix | Allyah | 2/6/13 | 2/14/13 | 0 | Current | Normal | In Trouble | true | false | false | Approval Not Required
16601 | 16601 Trilogy Floor Plan Browser - Edits | Allyah | 2/13/13 | 2/14/13 | 0 | Current | Normal | At Risk | true | false | false | Approval Not Required
16702 | CPCTV 16702 - Carmel The Village - Windmaster Update | Allyah | 2/22/13 | 2/19/13 | 54.5 | Current | Normal | On Target | true | false | false | Approval Not Required
16655 | MI 16655 - Mill Creek - Gulf Coast Southwest Construction Logo | Allyah | 2/19/13 | 2/19/13 | 75.6 | Current | Normal | On Target | true | false | false | Approval Not Required
16800 | CPRIV 16800 - Carmel Riverside - Fitness Center + Pool Rules Signs | Allyah | 2/19/13 | 2/18/13 | 34.3 | Current | Normal | At Risk | true | false | false | Approval Not Required
16850 | CPREN 16850 - Carmel - Renoir House - 3D Floor Plans | Allyah | 3/6/13 | 3/7/13 | 14 | Current | Normal | On Target | true | true | false | Approval Not Required
16901 | CP Carmel Partners - Riverside ¦ Madrid ¦ Bear Creek - Q1 Bootleg Replacement | Allyah | 2/15/13 | 2/15/13 | 18.6 | Current | Normal | On Target | true | false | false | Approval Not Required
16701 | CPPAC 16701 - Carmel Pacific Ridge - Flyer Update | Allyah | 2/20/13 | 2/20/13 | 61.7 | Current | Normal | On Target | true | false | false | Approval Not Required
17051 | WPAVY 17051 - The Avery Townhome - 2D Floor Plan | Allyah | 3/5/13 | 3/1/13 | 11.8 | Current | Normal | On Target | true | false | false | Approval Not Required
Account Manager: Chris Corbin (14)
1405 | BO 1405 Borger Corporate Responsive Website | Allyah | 3/27/13 | 3/14/13 | 54.3 | Current | Normal | On Target | true | true | true | Approval Not Required
6650 | MOVIG 6650 Village Green Copilot + Mobile | Allyah | 11/20/12 | 2/19/13 | 96.9 | Current | Normal | In Trouble | true | true | false | Approval Not Required
9100 | RM 9100 Royal American Corporate Site | Allyah | 4/12/13 | 4/17/13 | 65.9 | Current | Normal | At Risk | true | true | false | Approval Not Required
10501 | 10501 Park Newport Sign Design | Allyah | 2/25/13 | 2/22/13 | 14.3 | Current | Normal | At Risk | true | false | false | Approval Not Required
10702 | BRPPE 10702; Promenade Pointe - Property site Copilot | Allyah | 12/20/12 | 2/18/13 | 96.7 | Current | Normal | In Trouble | true | true | true | Approval Not Required
11003 | ATPNH 11003; Pinnacle at Nob Hill, CoPilot + Mobile + iPad+ SEO | Allyah | 2/6/13 | 2/13/13 | 95.2 | Current | Normal | In Trouble | true | true | true | Approval Not Required
11500 | DMJWA 11500 Jacobs Woods Apartments Copilot, Mobile & SEO | Allyah | 2/26/13 | 3/6/13 | 82.2 | Current | Normal | At Risk | true | true | true | Approval Not Required
11504 | DMBHP 11504 The Woods at Blue Heron Pines Copilot, Online App, Mobile, SEO Pro | Allyah | 2/28/13 | 3/8/13 | 62.2 | Current | Normal | At Risk | true | true | false | Approval Not Required
11502 | DMCAA 11502 College Arms Apartments Copilot, Online APP, Mobile, SEO | Allyah | 4/25/13 | 4/25/13 | 8.2 | Current | Normal | On Target | true | false | false | Approval Not Required
11952 | RVCAB 11952 RV_Berkeley Central_Copilot, Mobile, Splash, SEP Pro | Allyah | 2/19/13 | 2/26/13 | 86.9 | Current | Normal | At Risk | true | true | true | Approval Not Required
15052 | BOPTA 15052 Park Terrace & Crescent Apartments - Website + Mobile | Allyah | 2/21/13 | 3/8/13 | 6.3 | Current | Normal | At Risk | true | false | false | Approval Not Required
15062 | MX 15062 - 37 Properties - Website + Mobile + iPad +SEO Pro | Allyah | 4/2/13 | 4/2/13 | 22.8 | Current | Normal | On Target | true | true | false | Approval Not Required
15100 | PIFAH 15100 - 1550 Fahrenheit - Website + Mobile | Allyah | 3/5/13 | 3/5/13 | 64.8 | Current | Normal | At Risk | true | true | true | Approval Not Required
15500 | MX 15500 - Corporate - Web + Mobile - ON HOLD!! | Allyah | 2/11/13 | 2/12/13 | 81.3 | Current | Normal | In Trouble | true | false | false | Approval Not Required
Account Manager: Erica Cohen (8)
6752 | TCAST 6752 Alexan Sterling Ridge Copilot, Mobile, Floorplan Browser | Ian | 2/27/15 | 3/8/13 | 79.3 | Current | Normal | On Target | true | true | true | Approval Not Required
6753 | TCABR 6753 Alexan Briargate Copilot, Mobile, Floorplan Browser | Ian | 4/24/13 | 2/28/13 | 65.5 | Current | Normal | At Risk | true | true | false | Approval Not Required
6754 | TCADP 6754 Alexan Deer Park Copilot, Mobile, Floorplan Browser | Ian | 3/20/15 | 3/20/15 | 32 | Current | Normal | On Target | true | true | false | Approval Not Required
6951 | TCAOF 6951 Alexan Old Farm Copilot, Mobile, Floorplan Browser | Ian | 3/8/13 | 3/4/13 | 86.5 | Current | Normal | On Target | true | true | false | Approval Not Required
6950 | TCAFL 6950 Alexan Fountain Lake Copilot, Mobile, Floorplan Browser | Ian | 3/10/15 | 3/10/15 | 83.5 | Current | Normal | On Target | true | true | false | Approval Not Required
13600 | HGFSO 13600 HG Fenton Solterra Splash_Responsive Design_FPB_PPC_SEO_Email Marketing_3D Floorplans | Ian | 4/1/13 | 4/19/13 | 60.5 | Current | Normal | At Risk | true | true | true | Approval Not Required
14453 | TCAUC 14453 Alexan Urban Center CoPilot Website, Mobile, Floor Plan Browser, SEO | Ian | 3/27/13 | 3/29/13 | 69.3 | Current | Normal | At Risk | true | true | true | Approval Not Required
16450 | AR 16450: All Properties; Pay Rent Button | Ian | 2/15/13 | 2/15/13 | 0 | Current | Normal | At Risk | true | true | false | Approval Not Required
Ian

## Data List
Ref # | Name | Desc | Pln Comp | Proj Comp | %Comp | Status | Priority | Progress | Has Nts | Has Docs | Issues | Is Approval | Account Manager
6351 | WOAWS 6351 Alta Woodlake Square Copilot Splash + Website + Mobile | splash page this summer Full site - March 2013 Approved Home Page Design: http://code.l3as3labs.com/woodlakesquare/index2.html | 2013-02-21 | 2013-02-22 | 89.9 | Current | Normal | At Risk | true | true | true | Approval Not Required | Braedon Armstrong
6451 | WOAHI 6451 Alta Heights Copilot Splash + Website + Mobile | splash page this summer Full site - March 2013 | 2013-04-04 | 2013-04-04 | 18.6 | Current | Normal | At Risk | true | true | true | Approval Not Required | Braedon Armstrong
1911 | PW 1911 Property West Corp + Property Websites |  | 2013-01-31 | 2013-02-13 | 97.9 | Current | Normal | At Risk | true | true | true | Approval Not Required | Braedon Armstrong
1652 | ECRRG 1652 Regency Ridgegate Identity and Signage | -Logo Developemnt & Style Sheet -Campaign Concept -Stationary Package -Brochure -Floor Plans -Floor Plan Illustration -Signage | 2013-02-07 | 2013-02-12 | 96.5 | Current | Normal | In Trouble | true | true | true | Approval Not Required | Braedon Armstrong
2450 | MSTEN 2450 Pine Street Flats Phase 1 | Management Co: Brookside MS=Market Street 2450-1 Campaign Concept 2450-2 Site Map Illustration 2450-3 Signage | 2012-10-18 | 2013-02-12 | 99.6 | Current | Normal | On Target | true | true | false | Approval Not Required | Braedon Armstrong
2403 | SRPRV 2403 The Promenade Brochure & Stationery Design | DZAP to design a full color 9 x 16 (folded to 9 x 12) 12 page, saddle-stitch brochure featuring logo, floorplans, site plan, community amenities, location highlights and community and lifestyle photography. | 2013-02-14 | 2013-02-26 | 77.1 | Current | Normal | On Target | true | true | false | Approval Not Required | Braedon Armstrong
4750 | EC 4750 Echelon Corporate Refresh & New Residential Corporate Site |  | 2013-03-25 | 2013-03-22 | 84.8 | Current | Normal | On Target | true | true | false | Approval Not Required | Braedon Armstrong
5806 | BSWEP 5806 Woodland Estates | Brookside Woodland Estates Branding, Logo, campaign, brochure, 3d floorplans, site plan, signage | 2013-02-22 | 2013-02-18 | 84.7 | Current | Normal | At Risk | true | true | false | Approval Not Required | Braedon Armstrong
5809 | KC 5809 Klingbeil Property CoPilot + Mobile Websites | - 2 wireframes - 2 themes per wireframe (so 4 total themes) - 46 total properties - 1st steps needed are wireframes. - assume 2 weeks for each step for approval. IE 2 weeks for wireframe approval with 2 rounds of revisions in those 2 weeks. - assume 2 weeks home page approval with 2 rounds of revisions in there. - assume 3 weeks interior page approval with 2 rounds of revisions in there. - I am guessing the total project will be about 3-4 months. | 2013-04-12 | 2013-04-11 | 79.5 | Current | Normal | On Target | true | true | false | Approval Not Required | Braedon Armstrong
6052 | ECRRG 6052 Regency Ridgegate CoPilot Mobile | This needs to be opened asap we just presented campaign and need to get a splash page up | 2012-12-31 | 2013-02-11 | 100 | Current | Urgent | In Trouble | true | true | false | Approval Not Required | Braedon Armstrong
5654 | FCMAD 5654 First Communities Web + Mobile + iPad | Need to open job for management company First Communities and property Madison on the Green. Website, CoPilot , Mobile , iPad , Order Item(s) | 2012-10-08 | 2012-10-03 | 100 | Current | None | On Target | true | true | false | Approval Not Required | Braedon Armstrong
6350 | WOAAS 6350 Alta Alameda Station Copilot Splash + Website + Mobile | splash needed sometime in June full site - December 2012 | 2013-03-18 | 2013-03-18 | 77.9 | Current | Normal | On Target | true | true | false | Approval Not Required | Braedon Armstrong
6352 | WOALV 6352 Alta Lake Eve Copilot + Mobile | see project 6200 for Splash Page schedule | 2012-12-26 | 2013-02-11 | 100 | Current | Normal | On Target | true | true | false | Approval Not Required | Braedon Armstrong
9303 | FCAPL 9303 First Communities - Ashford Place | Need to set up property in CMS for client to upload. As well as set up mobile. Also has resident portal and Ipad as well ashfordplace-apartments.com | 2012-10-12 | 2013-02-12 | 95.9 | Current | Normal | In Trouble | true | true | false | Approval Not Required | Braedon Armstrong
9304 | FCBRC 9304 First Communities Briar Creek | Need to set up property in CMS and Mobile. Client will upload content. Also has resident portal and Ipad as well. Please use url briarcreek-apartments.com | 2012-10-12 | 2013-02-12 | 95.7 | Current | Normal | In Trouble | true | true | false | Approval Not Required | Braedon Armstrong
9305 | FCAVI 9305 First Communities - Ashford Villas | Need to set up property in CMS and Mobile. Client will upload content. This also has resident portal and Ipad as well. Please use url ashfordvillas.com | 2012-10-12 | 2013-02-12 | 96.4 | Current | Normal | In Trouble | true | true | false | Approval Not Required | Braedon Armstrong
9306 | FCSIP 9306 First Communities Sierra Place |  | 2012-10-15 | 2013-02-12 | 95.7 | Current | Normal | In Trouble | true | true | false | Approval Not Required | Braedon Armstrong
9504 | EC 9504 Echelon - Parker Hilltop - Rebranding | I need to open a job for Parker Hilltop Rebranding to include Brand and logo Development Website Homepage Design Brochure Design Ad Design and Email Marketing Template Signage Design These should include r rounds of revisions I need the Brand and Logo development to have the first date to the client on August 22nd David and Annika are aware of this and will make the deadline | 2013-01-29 | 2013-04-25 | 65.7 | Current | Normal | In Trouble | true | true | true | Approval Not Required | Braedon Armstrong
9800 | FCHAD 9800 First Communities - Hampton Downs - Copilot, Resident Portal, Mobile, iPad | I need to set up a job with the property being set up in CMS for client to upload content. I also need mobile and Ipad to begin after the property has been set up in CMS We will need to set up our resident portal for them as well | 2013-02-27 | 2013-02-14 | 94.4 | Current | Normal | On Target | true | true | true | Approval Not Required | Braedon Armstrong
9801 | FCSIR 9801 First Communities - Sienna Ridge | I need to set up a job with the property being set up in CMS for client to upload content. I also need mobile and Ipad to begin after the property has been set up in CMS We will need to set up our resident portal for them as well | 2013-02-12 | 2013-07-23 | 52.5 | Current | Normal | At Risk | true | true | true | Approval Not Required | Braedon Armstrong
10002 | JMVEL 10002 JMG - Villages of Eastlake ¦ Brochure ¦ Letterhead | DZAP to design letterhead plus #10 envelope, Brochure folder with 2 insert pockets and business card slot. Includes 2 concepts + 1 round of revision + 1 round refinement on selcted concept | 2013-02-05 | 2013-02-12 | 95.7 | Current | Normal | In Trouble | true | true | false | Approval Not Required | Braedon Armstrong
10203 | SRCYP 10203 Sares Regis - Canyon Park brochure | DZAP to design a full color 8 pannel tri-fold brochure featuring logo, floorplans, site plan, community amenities, location highlights, and community and lifestyle photographs Based off of the Ironwood Brochure 8.5 x 14 fold to 3.66 x 8.5 4/4 8 panel, tri-fold 8-# Silk Cover | 2013-01-02 | 2013-02-13 | 92.6 | Current | Normal | In Trouble | true | false | false | Approval Not Required | Braedon Armstrong
11451 | PWBHH 11451 Property West - Hawaii House | We will be building a website on our CMS designed specifically for the house property west owns and rents in Hawaii. This will also have mobile | 2015-03-18 | 2015-03-17 | 1.2 | Current | Normal | On Target | true | false | false | Approval Not Required | Braedon Armstrong
12800 | FCACE 12800 First Communities - Amber Chase - CMS - Resident Portal- Mobile - iPad - SEO | I need the job opened for CMS upload of a property with us uploading content. We will also need Mobile and iPad | 2012-12-13 | 2013-02-13 | 72.6 | Current | Normal | In Trouble | true | true | true | Approval Not Required | Braedon Armstrong
13150 | 13150 Whiteco - 5250 Houston - CoPilot - Mobile - Splash Page - SEO | Approved Home Page: http://code.l3as3labs.com/5250apts/index2.html | 2013-03-28 | 2013-03-22 | 72.8 | Current | Normal | On Target | true | true | false | Approval Not Required | Braedon Armstrong
13350 | ECPKH_13350_Parker Hilltop_Copilot | We need to open a job for copilot | 2013-03-25 | 2013-03-28 | 62.6 | Current | Normal | On Target | true | false | false | Approval Not Required | Braedon Armstrong
14004 | FCALA 14004 First Communities - Asford Lake Apartments - CoPilot, Resident Portal, Mobile, Ipad | This will be built using the same template as the radico sites. (Ashford Villas) | 2012-12-14 | 2013-02-20 | 73.5 | Current | Normal | In Trouble | true | true | false | Approval Not Required | Braedon Armstrong
14000 | STVAG 14000 Stonemark - Radico - Villas at Ashford Gardens - copilot - mobile |  | 2013-02-07 | 2013-02-22 | 87 | Current | Normal | In Trouble | true | false | false | Approval Not Required | Braedon Armstrong
14002 | STASP 14002 Stonemark - Radico - Ashford Pavilion - CoPilot - Mobile | Set up on temp theme - (Ashford Villas) | 2012-12-04 | 2013-02-25 | 16.7 | Current | Normal | In Trouble | true | false | false | Approval Not Required | Braedon Armstrong
14001 | STASM 14001 Stonemark - Radico - Ashford Meadows - CoPilot - Mobile | Set up on temp theme (Asford Villas) | 2012-12-04 | 2013-02-25 | 16.7 | Current | Normal | In Trouble | true | true | false | Approval Not Required | Braedon Armstrong
14003 | SRRIO 14003 Sares Regis - The Lofts at Rio Salado - VIP Cards | I need to have a full color vip card designed with 1 round of revisions. | 2012-11-30 | 2013-02-12 | 82.9 | Current | Normal | In Trouble | true | false | false | Approval Not Required | Braedon Armstrong
14102 | 14102 Wood Partners - Creek Side Brochure | Shane to send client designed brochure into production. Need a folder on the server for art work. | 2012-11-30 | 2013-02-22 | 23.2 | Current | Normal | In Trouble | true | false | false | Approval Not Required | Braedon Armstrong
14205 | First Communities - 14205 - Ivy Hall Apartments - Copilot - Mobile - iPad - Resident Portal - Seo | We need to set this job up to be a full design site. It will be based off of the first communities wireframe but will have its own design. This site will include resident portal, mobile, ipad and seo | 2013-02-18 | 2013-02-28 | 72.8 | Current | Normal | At Risk | true | true | true | Approval Not Required | Braedon Armstrong
14351 | Stonemark 14351 - Radico - Ashford Gardens - CMS - Mobile | Please set this up on the same theme as ashford villas but under stone mark. We will upload content not the client | 2013-01-18 | 2013-02-15 | 41.3 | Current | Urgent | In Trouble | true | false | false | Approval Not Required | Braedon Armstrong
15000 | BR 15000 Bonaventure - 14 Properties - Website + Mobile + iPad | ▪ Same Wireframe as Promenade Point @ http://bonaventure-staging.com/promenade-pointe/ ▪ Each site to have own theme. (Includes 2 designs and 2 rounds of revision.) ▪ Re - write copy (David) ▪ Scrape sites for input forms (Chris) ▪ Assets, Creative forms, etc… to be completed by Jan 1 (Chris) This project includes 14 properties: 1 - BRENA - The Encore - http://code.l3as3labs.com/theencore (HP PENDING APPROVAL V1/R2) 2 - BRGLA - Glen Arbor - http://code.l3as3labs.com/glenarbor (HP APPROVED) 3 - BRRWP - Rockwood Park - http://code.l3as3labs.com/rockwoodpark (HP PENDING APPROVAL V1/R1) 4 - BRCAH - Carriage Hill - http://code.l3as3labs.com/carriagehill (HP PENDING APPROVAL V1/R1) 5 - BROAK - Oak Lake - http://code.l3as3labs.com/oaklakes (HP PENDING APPROVAL V1/R2) 6 - BRIVY - Ivystone - http://code.l3as3labs.com/ivystone (INTERIORS COMPLETE) 7 - BRBRF - Brookfield - http://code.l3as3labs.com/brookfield (HP PENDING APPROVAL V1/R1) 8 - BRMAG - Magnolia Run - http://code.l3as3labs.com/magnoliarun (HP APPROVED) 9 - BRSTC - St. Croix - http://code.l3as3labs.com/stcroix (HP PENDING APPROVAL V1/R1) 10 - BRCAS - The Cascades - http://code.l3as3labs.com/cascades (INTERIORS COMPLETE) 11 - BRWDV - Woodview - http://code.l3as3labs.com/woodview (HP PENDING APPROVAL V1/R1) 12 - BRCRV - Crowfield Village - http://code.l3as3labs.com/crowfield (HP APPROVED) 13 - BRCDR - Cedar Grove - http://code.l3as3labs.com/cedargrove (HP APPROVED) 14 - BRWSG - Windsong - http://code.l3as3labs.com/windsong (HP AWAITING FEEDBACK V1/R1) V = Version R = Round | 2013-03-22 | 2013-03-22 | 58.2 | Current | Normal | On Target | true | true | true | Approval Not Required | Braedon Armstrong
14550 | WOALA 14550 - Alta Warner Website + Mobile + SEO | Info to come. | 2013-02-28 | 2013-02-28 | 57.1 | Current | Normal | On Target | true | true | false | Approval Not Required | Braedon Armstrong
14659 | FCWRU 14659 First Communities - Walden Run - CoPilot - Mobile - iPad - E-Brochure - SEO | We need to set this job up to be a full design site. It will be based off of the first communities wireframe but will have its own design. This site will include resident portal, mobile, ipad and seo | 2013-02-25 | 2013-03-06 | 55.3 | Current | Normal | At Risk | true | true | false | Approval Not Required | Braedon Armstrong
15702 | BSPSF 15702 - Pine Street Flats - Floor Plan Browser | Dzap to create a interactive floorplan map for Pine Street Flats. They will be using property link feeds. Folder located at: afp://dzapsrv2._afpovertcp._tcp.local/Active/BSPSF_15702_Pine_Street_Flats_Floor_Plan_Browser | 2013-04-03 | 2013-04-22 | 0.2 | Current | Normal | At Risk | true | false | false | Approval Not Required | Braedon Armstrong
15703 | FCEWV 15703 - First Communities - Edgewater Vista - CMS Website + Resident Portal | :: Details: :: - Set up Edgewater Vista on the existing Prop Romano Green - AM to upload content - Scope of Work Doc to come Domain: TBA Folder located at: afp://dzapsrv2._afpovertcp._tcp.local/Active/FCEWV_15703_First_Communities_Edgewater_Vista_CMS_Website_Resident_Portal | 2013-01-29 | 2013-02-21 | 11 | Current | Normal | In Trouble | true | false | false | Approval Not Required | Braedon Armstrong
15700 | AS 15700 - Asher Investments - Responsive Design + SEO | :: Project Details :: ▪ We also need to start SEO on the properties as soon as possible. SEO will be 5 keywords per each property (Braedon working with Jori from SEO Haus) ▪ We are going to change over all the Asher sites to responsive design. There will not need to be any design time this will all be development. Development does not need to start until we have the capacity with our schedule to begin. We will revisit the responsive design in April. Asher Investment Properties: ▪ Amberwood ▪ Broadfalls ▪ Churchills Choice ▪ Cobblestone Hill ▪ Eagle Crest ▪ Eagles Landing ▪ Fox Creek ▪ Foxfire ▪ Hawthorne Hill ▪ Hermitage HIll ▪ Hunter's Ridge ▪ Huntington Downs ▪ Panorama at Arvada Ridge ▪ Stonebridge at Twin Peaks ▪ Summerwind ▪ The Glen ▪ Vistas at Stony Creek ▪ Washington Park ▪ Water's Edge Apartments ▪ Whetstone ▪ Yukon Court ▪ The 3 themes: ▪ http://www.watersedgedenver.com/ ▪ http://www.asherinvgroup.com/hunters-ridge ▪ http://www.asherinvgroup.com/foxfire | 2013-04-17 | 2013-04-17 | 0.2 | Current | Normal | On Target | true | true | false | Approval Not Required | Braedon Armstrong
15855 | GR 15855 - Greystone - 6 New Properties - CMS Set Up | We need to set up 6 new properties for content upload. This will go on the existing Greystone theme. Once content is uploaded it will need to be added to the corporate site. :: Tasks :: ▪ Setup new CMS account using Greystone theme ▪ Upload client provided content ▪ Add to corporate property Folder located at: afp://dzapsrv2._afpovertcp._tcp.local/Active/GR_15855_Greystone_6_New_Properties_CMS_Set_Up :: Properties :: ▪ Country Club Apartments ▪ The Woodlands Apartments ▪ Spring Hollow Apartments ▪ Hawthorne Hills Apartments ▪ Ashley Club Apartments ▪ Arbor Club Apartments | 2013-02-14 | 2013-02-19 | 79.8 | Current | Normal | At Risk | true | false | false | Approval Not Required | Braedon Armstrong
16150 | CR 16150 - Compass Rock - Riverton Square - Website + Mobile | Need to open a project for a full site for a single property to include middle, Folder located at: afp://dzapsrv2._afpovertcp._tcp.local/Active/CR_16150_Compass_Rock_Riverton_Square_Website_Mobile | 2013-04-04 | 2013-04-15 | 12.3 | Current | Normal | At Risk | true | false | false | Approval Not Required | Braedon Armstrong
16550 | FC 16550 First Communities - Century - Century Trinity Estates -CMS - Mobile - SEO | Please set up a schedule for Century Trinity Estates. This will need to be set up in the CMS under the century theme. We will upload some content but the client will upload most. Please also set up schedule for Mobile and SEO | 2013-02-26 | 2013-02-14 | 74.2 | Current | Normal | On Target | true | true | true | Approval Not Required | Braedon Armstrong
16652 | AAVAR 16652 AGI - Vara - Responsive Design Full Website | We will be laying out a custom full design responsive design site. | 2013-04-25 | 2013-05-03 | 1.3 | Current | Normal | At Risk | true | false | false | Approval Not Required | Braedon Armstrong
16654 | BM- 16654 Briarcliff Management - Corporate site - 2 Properties - resident portal - online app - ipad - mobile - SEO | BM - 16253 Briarcliff Management - Corporate site - 2 Properties - resident portal - online app - ipad - mobile - SEO Description We need to open a job to include building a new design for corporate site and 2 property sites. Each property will have its own theme. Property sites will also include ipad, mobile, seo, resident portal, and online application Property names Colonial Village and Coach and Carriage House | 2013-04-19 | 2013-04-18 | 4.6 | Current | Normal | On Target | true | true | false | Approval Not Required | Braedon Armstrong
16750 | STASM 16750 Radco - Ashford at Geneva | We need to upen a job for a website on an existing theme. This will be cms upload and mobile only. This site will go on the Meadow wood village theme. | 2013-02-28 | 2013-02-28 | 4.9 | Current | Normal | On Target | true | false | false | Approval Not Required | Braedon Armstrong
16950 | WOVario 16950 Wood Partners - Alta Woodlake-Alta Alameda Station Floorplans | Dzap to layout 2D floorplans Woodlake - 22 plans Alameda - 28 floorplans These will be based off of altacreekside.com plans | 2013-03-01 | 2013-03-01 | 11.8 | Current | Normal | On Target | true | false | false | Approval Not Required | Braedon Armstrong
8959 | CPCTV 8959 Carmel The Village Launch Responsive | We'll be launching Carmel The Village this fall. here are the items we need to schedule with notes and desired delivery dates: Carmel Luxury Themed Website, Ipad, Mobile - use the carmelpacificridge.com wireframe; NEW theme - client wants to launch October 1 Splash page - use the carmelpacificridge.com splash page template; NEW theme - client wants to launch mid-August if we can. 3D Floorplans - eight 3D plans - need to deliver in the next two weeks Site Map - need to complete by early September Location Map - need to complete by early September Marketing Slide Show - need to complete by late September Stationery, Business Card + Add Business Card to EZPublish - need to deliver to the property by late September - need to program on EZP by early September Outreach Collateral - 2 half page flyers and bookmark - deliver late september Email Marketing - 4 header images and set up - set up by late September | 2013-02-04 | 2013-02-08 | 100 | Current | Normal | In Trouble | true | true | false | Approval Not Required | Jenny Hill
1552 | GATWY 1552 Gateway Apts & Townhomes Brochure | Provide job jacket to Jenny - has yet to do creative brief of kick off meeting with the client. Schedule to be adjusted | 2013-02-21 | 2013-02-12 | 62.5 | Current | Normal | At Risk | true | true | false | Approval Not Required | Jenny Hill
2301 | KFVIN 2301 1600 Vine Brand Identity + Campaign Theme | BRAND IDENTITY: LOGO DEVELOPMENT AND PROPERTY THEME ¦ DZAP to develop community brand identity: | 2013-02-12 | 2013-02-12 | 94.6 | Current | Normal | On Target | true | true | true | Approval Not Required | Jenny Hill
4151 | LEVIS 4151 1600 Vine CoPilot Website | http://www.1600vine.com/ 1. Transfer hosting of existing site 1a. complete changes outlined in tasks DNA is the current website host and has a dropbox where all of the digital files are stored. Website and Marketing files from DNA http://dna-inc.com/1600vine/ user: guest pass: 1600vineDocs 2. Create a new copilot website using a similar theme to concordmews.com. 2a. feature set to include the following items: day/night transition, google translate, mobile theme, link to video tour, one touch savings and service link, facebook, twitter, walk score, pin it, ebrochure, and SEO. | 2012-12-13 | 2013-01-03 | 100 | Current | Normal | In Trouble | true | true | false | Approval Not Required | Jenny Hill
5808 | AERPK 5808 AMLI Riverfront Park Signage | - full signage package. - was previously opened in Basecamp with job # 04707. - working in conjunction with ad light on signage concepts. - ad light has already started on monument concepting. - next steps is for us to layout the unit ID, rules sign samples. - please assign to me for a creative brief and kick off meeting. | 2013-02-18 | 2013-02-19 | 81.7 | Current | Normal | At Risk | true | true | false | Approval Not Required | Jenny Hill
5901 | WR 5901 Woodmont Sobrato Theme | DZAP LeaseLabs™ to design and develop a new property website theme to accomplish the goals outlined in the Sobrato revamp document and highlighted below. - Intuitive and seamless display of Online Leasing (Vaultware) - Minimal scrolling, keeping info above fold - Navigation across the top, must start with Floor Plans and Pricing - Enable prospect to make appointments for apartment showing - Branding ‐ does not need Woodmont branding - Responsive Design – site should be adaptable to all devices - Vanity URL Masking - Dynamic Site Map similar to www.alexangarrettfarms.com - Site map design for each property (5) DZAP to provide two (2) rounds of revisions to design concepts. Additional rounds to be billed at DZAP hourly rate of $120. Theme to be used on Sobrato portfolio exclusively. Moving additional properties to this new theme would result in additional costs depending on scope and volume. Interactive Site Maps cost do not include Site Map design. Site map design, if needed will incur charges of $750 - $1500 depending on size and layout of property. This is ONE theme to be applied to five properties. Goal is 100% design approval by May 30. We can move to programming after that. We'll also be doing an advanced floorplan selector tool for each one. | 2013-02-19 | 2013-03-04 | 97 | Current | Normal | At Risk | true | true | false | Approval Not Required | Jenny Hill
6955 | MITRI 6955 Trilogy Website Copilot Site, Splash Page, Floorplan Browser |  | 2013-02-08 | 2013-02-14 | 97.4 | Current | Normal | On Target | true | true | true | Approval Not Required | Jenny Hill
9702 | LCTAS 9702 LCOR: 121 Tasman, Branding Package | 1) Branding & Logo Development -concept presentation consists of 2 concepts including: 4 initial logo options, ads or direct mail, marketing signage, website splash page and stationary package. Includes 2 rounds of revisions and 1 round of refinements. Final deliverable is PDF package with concepts for above elements. -Upon approval of brand identity, Dzap to develope Brand Style guide, which includes final logo with color designations for single color, full color, black and white versions, logo usage guidelines, color palette and font specifications. 2)Brochure/Takeaway Design -Dzap to layout a double sided, full page color brochure/takeaway based on concept selection. 2 rounds of revisions and 1 round of refinements and print production management. 3)Ad Design, Craigslist & Email Marketing Template -Dzap to design a full page, 1/2 page, facebook style flyer/ad layout, 5 craigslist html templates and an email-marketing template based on approved campaign theme. Flyers may be programmed into EZPublish. 2 rounds of revisions and 1 round of refinements. 4)Promotional Items -Dzap to design waterbottle wraps, bookmark, gumvelope for brand launch andplace items on EZPublish for simple ordering. Files to be delivered as editable PDF's. 2 rounds of revisions and 1 round of refinements. 5)Miscellaneous items -Dzap to design site map illustration, vicinity map illustration, e-brochure, construction phase banner, aframe signage (2) and toppers (10), fence/building banners (2 versions) all based on approved campaign. Dzap to create pruction ready stationary files (business cards, letterhead/envelope, notecard/envelope). 2 rounds of revisions and 1 round of refinements. | 2013-02-08 | 2013-02-25 | 64.2 | Current | Normal | In Trouble | true | true | false | Approval Not Required | Jenny Hill
10657 | WA 10657 Wasatch Responsive Design Website | MUST LAUNCH BY END OF JANUARY NEED STAGING LINKS EARLY JANUARY - see attached for full scope - responsive design site - new corporate site for isyourhome.com - new landing pages - 3 NEW themes + adapting the Four Seasons theme to be responsive design - NO MOBILE OR IPAD - minimal copy writing, if any is needed - ADA compliant Feature Sets: Corporate Site Feature Set • Company introduction • Search by community name and city • Photography slide show • Featured property / social networking / video • About / contact us pages • Link to chat provider • Regional landing pages o Interactive Google map displaying property locations o Property list including “hero” photo, contact information, starting from rent (through 3rd party MITS feed). Property Sites Feature Set • Home Page o Introductory updatable “romance” paragraph / SEO copy o Photo slide show and link to photo gallery o Contact information o Specials (through 3rd party MITS feed) o Easy to update graphic space for specials and announcements o Social media integration to Facebook/Twitter/YouTube/+One/Others • Floorplans page o Floorplans - thumbnails with the ability to view large o Pricing (through 3rd party MITS feed) o Link to online lease/check availability o Printable / emailable ebrochure per floorplan • Amenities page o Photo slide show o Detailed, appealing amenity list • Location page o Detailed, interactive Google location map o Points of Interest in various categories with direct links to enhance SEO • Contact us o Contact information / contact us form • My Wasatch o Pay rent online link o Service request form o Calendar o Newsletter PDF o Concierge • All pages o Media gallery showcasing large photography, video o Share / text / email a friend o Updatable SEO copy o Link to chat provider o Refer a friend o Testimonials link o PDF application / optional online application | 2013-02-19 | 2013-02-19 | 87.9 | Current | Normal | At Risk | true | true | true | Approval Not Required | Jenny Hill
12450 | CPSOL 12450 Solstice Launch Website + Mobile | create the following items: - campaign + logo concept (see attached for schedule) - upon logo approval: - design and program a splash page - design and program a website based on therambleapartments.com (including mobile theme) - email marketing set up - 4 templates - stationery package - program stationery package on ezp - outreach flyer/bookmark - large tri fold brochure - 4 3-D floor plans - Bootleg and windmaster insert | 2013-12-05 | 2013-02-01 | 100 | Current | Normal | On Target | true | true | false | Approval Not Required | Jenny Hill
12600 | WA 12600 Portal Refresh | Launch date: 2/4 | 2013-04-15 | 2013-05-16 | 52.3 | Current | High | On Target | true | true | false | Approval Not Required | Jenny Hill
13602 | 13602 LEVIN 1600 Vine Stationery | please typeset the approved cards Augustine Um Business Manager AUm@LegacyPartners.com Shaylon Mitchell Assistant Business Manager SMitchell@LegacyPartners.com Timothy LaBrier Maintenance Manager TLaBrier@LegacyPartners.com Jorge Argueta Maintenance Technician JArgueta@LegacyPartners.com Melanie Gosch Leasing Manager MGosch@LegacyPartners.com Nelson Bennett Leasing Manager / Quality Control NBennett@LegacyPartners.com Kiley Speakman Leasing Consultant KSpeakman@LegacyPartners.com Melanie Valdez Receptionist MValdez@LegacyPartners.com For the letterhead the information is currently listed in this order; 1600 North Vine, Hollywood CA 90028 P: 323.462.0400 F: 323.462.0401 www.1600VINE.com | 2013-02-11 | 2013-02-13 | 65.7 | Current | Normal | In Trouble | true | false | false | Approval Not Required | Jenny Hill
14051 | CP 14051 Carmel Midtown Square 12 page brochure | - use carmel 12 page format - see input folder for creative brief - goal is to print this brochure with another 12 page carmel brochure for volume print discount, thus, print date is TBD | 2013-02-08 | 2013-02-20 | 44.5 | Current | Normal | In Trouble | true | false | true | Approval Not Required | Jenny Hill
14452 | CP 14452 Carmel Midtown Square window graphics | design graphics for windows at the leasing center see full creative for details client will coordinate print and install with vendor | 2013-02-01 | 2013-02-15 | 52.3 | Current | Normal | In Trouble | true | false | false | Approval Not Required | Jenny Hill
14407 | 21100 Trilogy Dynamic Email | I just called Yardi to confirm this, but below and attached should be everything you need to set up DNI on our property website. If you have any questions or need support, please reach out to Chase Miller at Yardi at 888-622-9889. trilogynoma.com These set of task have been created for Issue 21100 Please see issue if you need more details: https://dzap.attask-ondemand.com/issue/view?ID=508eab28000043a1c46151022e478ff1 | 2013-02-11 | 2013-02-12 | 28.6 | Current | Normal | On Target | true | true | false | Approval Not Required | Jenny Hill
14752 | RVMOM 14752 Modera Miramar Green Living page | http://www.carmelapartments.com/carmel-waterfront-apartments we need to design, write copy for and build a green living page for modera miramar. we originally did this for concordmews.com but ended up hiding the button. however, we can use the same layout for the modera site. I will add a full brief to the server when the job is opened. | 2012-12-27 | 2013-02-15 | 16.6 | Current | Normal | In Trouble | true | true | false | Approval Not Required | Jenny Hill
14903 | CPWHI 14903 Carmel: Waterfront at Puuloa Floor plan display | - see full creative brief for details. - DZAP to do art and coordinate production. | 2013-02-01 | 2013-02-01 | 100 | Current | Normal | On Target | true | true | false | Approval Not Required | Jenny Hill
15050 | CP 15050 Carmel Midtown Square 3D floor plans | 12 - 3D floor plans see creative brief | 2013-02-21 | 2013-02-28 | 37.2 | Current | Normal | At Risk | true | true | false | Approval Not Required | Jenny Hill
15051 | CPERI 15051 Carmel Hacienda Heights Brochure | - design a 12 page brochure using the carmel format - quote already completed - will print with the carmel midtown square brochure - see creative brief for full details | 2013-01-30 | 2013-02-12 | 70.8 | Current | Normal | In Trouble | true | false | false | Approval Not Required | Jenny Hill
15057 | CPCHW 15057 Carmel Midtown Square Site Map | - see creative brief for details. | 2013-02-07 | 2013-02-12 | 77.1 | Current | Normal | In Trouble | true | true | false | Approval Not Required | Jenny Hill
15058 | CPCTV 15058 Carmel The Village 11x17 site map | - see full creative brief for all details - will need to blow up the size of the map to fit on an 11x17 sheet and include the units, logo, contact info - need a print quote | 2013-02-12 | 2013-02-20 | 55 | Current | Normal | At Risk | true | false | false | Approval Not Required | Jenny Hill
15150 | CPDEN 15150 Carmel Q1 2013 Campaign | - use the Q4 template to set up this project - creative + web - see full creative brief - need to launch campaign online on Jan 2. - need creative to deliver as quick as we can. - Ideally we'll have all creative approved by Friday since I'll be out next week! | 2013-03-25 | 2013-03-25 | 87.9 | Current | Normal | On Target | true | true | false | Approval Not Required | Jenny Hill
15600 | CPCTV 15600 - Carmel The Village - Video | - start the schedule after the new year - full creative brief to be added to the server - tasks: photo selection/story boarding client review and approval - 2 rounds music selection client review and approval - 1 round production send file to client Folder at: afp://dzapsrv2._afpovertcp._tcp.local/Active/CPCTV_15600_Carmel_The_Village_Video | 2013-03-07 | 2013-03-13 | 19.4 | Current | Normal | At Risk | true | false | false | Approval Not Required | Jenny Hill
15551 | CPPAC 15551 - Carmel Pacific Ridge - Video | Start the schedule after the new year Full creative brief to be added to the server :: Tasks :: - photo selection/story boarding - client review and approval - 2 rounds - music selection - client review and approval - 1 round - production - send file to client Folder at: afp://dzapsrv2._afpovertcp._tcp.local/Active/CPPAC_15551_Carmel_Pacific_Ridge_Video | 2013-03-06 | 2013-03-15 | 16.3 | Current | Normal | At Risk | true | false | false | Approval Not Required | Jenny Hill
15706 | CPWES 15706 Westwood brochure | - pick up art from existing brochure - update colors, photos and copy per creative brief | 2013-02-08 | 2013-02-12 | 94.5 | Current | Normal | In Trouble | true | true | false | Approval Not Required | Jenny Hill
15704 | 15704 Ramble Brochure | - pick up art from existing brochure - complete edits including photo and text edits | 2013-02-21 | 2013-02-21 | 64.6 | Current | Normal | On Target | true | true | false | Approval Not Required | Jenny Hill
15851 | CPVA 15851 Bear Valley Temp Brochure + Illustrations | please open a job with 3 sets of tasks/subtasks: temporary brochure for print 3D floor plans Site plan | 2013-03-01 | 2013-02-26 | 43.9 | Current | Normal | On Target | true | true | true | Approval Not Required | Jenny Hill
16100 | CPVUE 16100 Carmel Vue keychain reorder | client would like to reorder 100 of the attached key chains for Carmel Vue. we should ask shane to pull past orders so we can see if we can just pick up existing creative. | 2013-02-01 | 2013-02-07 | 100 | Current | Normal | In Trouble | true | true | false | Approval Not Required | Jenny Hill
16101 | LCTAS 16101 121 Tasman Flyers | create 3 flyers total: - double sided full page - 1/2 page outreach - facebook full page flyer see full creative brief for details | 2013-02-18 | 2013-02-18 | 14.8 | Current | Normal | At Risk | true | true | false | Approval Not Required | Jenny Hill
16103 | WODSM 16103 Alta San Marcos Website + Mobile | http://www.altasanmarcos.com/san-marcos we'll be redoing this website to match the wireframe for domainoakland.com http://domainoakland.com/domain kick off call with the client is 1/16 | 2013-02-15 | 2013-02-27 | 36.6 | Current | Normal | At Risk | true | true | false | Approval Not Required | Jenny Hill
16200 | LeaseLabs Website - 16200 | - design + program a new Lease Labs website - open project using the corporate website theme attask project template - will be responsive - target launch date is Feb 18. | 2013-02-19 | 2013-02-26 | 24.4 | Current | Normal | At Risk | true | false | false | Approval Not Required | Jenny Hill
16303 | CPCTV 16303 Carmel The Village stickers | 2.5" Diameter Circular Stickers Printed on White Gloss Stock min quantity is 1000 2 Color (perfect for CPCTV Logo) 1000: $178 content: Carmel The Village logo CarmelTheVillage.com 650.948.4512 | 2013-02-05 | 2013-02-14 | 92.6 | Current | Normal | In Trouble | true | false | false | Approval Not Required | Jenny Hill
16302 | CPMAD 16302 Carmel: Madrid no glass allowed sign | create a sign with the following verbiage: no glass allowed in pool area qty = 2 use job 14601 as a reference for the style and size of the sign. | 2013-02-14 | 2013-02-12 | 92.6 | Current | Normal | On Target | true | false | false | Approval Not Required | Jenny Hill
16400 | CPSOL 16400 Solstice brochure | large tri fold brochure see full creative brief on the server | 2013-02-19 | 2013-02-21 | 35 | Current | Normal | At Risk | true | false | true | Approval Not Required | Jenny Hill
16500 | CPWVI 16500 West Village mailer insert | create a mailer insert ad for West Village. -Physical mailer 8 1/2 x 3 3/5 Deadline February 8th here is an overview in brief. * Where the ad will be seen/displayed? * The mailer will be placed inside a magazine that goes out to all members of the alumni association. (includes current students and parents of current students) * Are there paper requirements? Is our standard flyer paper okay? * Besides the size requirement nothing else was mentioned. I have attached a mailer they provided me as an example. The mailer was printed on glossy paper. * What is the message? * The message should be simple, "We are West Village home of Viridian, Solstice and The Ramble Apartments and provide knowledge that we are a zero net energy community and include contact information. * What are the ad requirements (photo, QR code, etc?) * Include an image of our property, all four logos, contact information (phone, email, irio qr code, website) | 2013-02-11 | 2013-02-12 | 89.4 | Current | Normal | In Trouble | true | true | false | Approval Not Required | Jenny Hill
16651 | 16651 -1600 Vine Website Fix | 1600vine.com Lee, Erica and I met to discuss the 1600 Vine Website fix today. we need to turn this issue into a set of tasks for Lee and myself: - Programming fixes - Staging link to client - Client approval - Go live Lee is going to start work on this today and it will take him 2-3 days to complete this work. target go live date is 2/6 | 2013-02-06 | 2013-02-14 | 0 | Current | Normal | In Trouble | true | false | false | Approval Not Required | Jenny Hill
16601 | 16601 Trilogy Floor Plan Browser - Edits | Hi Patricia: We need to convert this issue into a set of tasks for: Programming edits Staging link to client Client approval Go live http://www.trilogynoma.com/trilogy-noma/floorplan-browser Edits 1. Add another radio button for "all" when selecting floor plan type. 2. Change the white copy in the Linq section to the same gray shade that appears in the yellow buttons. 3. Change the error message that appears when a search criteria doesn't yield any results For the error message, please use this: Whoops! We weren’t able to find any apartments that match your search exactly. Please try a different search to see other available apartments. Thank you! | 2013-02-13 | 2013-02-14 | 0 | Current | Normal | At Risk | true | false | false | Approval Not Required | Jenny Hill
16702 | CPCTV 16702 - Carmel The Village - Windmaster Update | Instructions: Pick up art from job 14151 and complete the following edits Include "LEASING PARKING" with 2 arrows below pointing in opposite directions. Folder at: afp://dzapsrv2._afpovertcp._tcp.local/Active/CPCTV_16702_ Carmel_The_Village_ Windmaster_Update | 2013-02-22 | 2013-02-19 | 54.5 | Current | Normal | On Target | true | false | false | Approval Not Required | Jenny Hill
16655 | MI 16655 - Mill Creek - Gulf Coast Southwest Construction Logo | Project Details: Create a logo for the following entity using the Mill Creek construction template: Mill Creek Gulf Coast Southwest Construction 1st draft due on 2/6. Upon client approval, we need to add it to their EZP account. Folder Location: afp://dzapsrv2._afpovertcp._tcp.local/Active/MI_16655_Mill_Creek_Gulf_Coast_Construction_Logo | 2013-02-19 | 2013-02-19 | 75.6 | Current | Normal | On Target | true | false | false | Approval Not Required | Jenny Hill
16800 | CPRIV 16800 - Carmel Riverside - Fitness Center + Pool Rules Signs | Shane provided a cost for the editing and production of the fitness center and pool rules signs for Riverside. This was bid with Ad light and pricing is below. Pool Rules - $438 Fitness Rules - $354 Ad Light has agreed to update the creative for us so we don't need to schedule creative time for our team. Here are the edits for ad light: We need "children" replaced with "persons" and the fitness center age to be 14, 16 for pool rules. We will need one round of creative approval for the client . Folder located at afp://dzapsrv2._afpovertcp._tcp.local/Active/CPRIV_16800_Carmel Riverside_Fitness_Center _Pool_Rules_Signs | 2013-02-19 | 2013-02-18 | 34.3 | Current | Normal | At Risk | true | false | false | Approval Not Required | Jenny Hill
16850 | CPREN 16850 - Carmel - Renoir House - 3D Floor Plans | Details: Design 11 3D floorplans Folder Location: afp://dzapsrv2._afpovertcp._tcp.local/Active/CPREN_16850_Carmel_Renoir House_3D_Floor_Plans | 2013-03-06 | 2013-03-07 | 14 | Current | Normal | On Target | true | true | false | Approval Not Required | Jenny Hill
16901 | CP Carmel Partners - Riverside ¦ Madrid ¦ Bear Creek - Q1 Bootleg Replacement | One of the Q1 bootlegs walked away from The Madrid this week. Can we get them a replacement? No changes to art. Riverside Madrid Bear Creek Folder Location: afp://dzapsrv2._afpovertcp._tcp.local/Active/CP_Carmel_Partners_Riverside_Madrid_Bear_Creek_Q1_Bootleg_Replacement | 2013-02-15 | 2013-02-15 | 18.6 | Current | Normal | On Target | true | false | false | Approval Not Required | Jenny Hill
16701 | CPPAC 16701 - Carmel Pacific Ridge - Flyer Update | Pick up art from job 11702 We need to have this flyer updated to use for the upcoming Expo. 4 Weeks Free! Lease & Receive a $150 Gift Card! Plus, Free Storage for a Year! Pay No Application Fees! The dates should also be included on the flyer: Open House February 21st- March 1st. We also need to add the MSG&DATA RATES MAY APPLY verbiage to the flyer for IRIO. Folder Location: afp://dzapsrv2._afpovertcp._tcp.local/Active/CPPAC_16701_Carmel_Pacific_Ridge_Flyer_Update | 2013-02-20 | 2013-02-20 | 61.7 | Current | Normal | On Target | true | false | false | Approval Not Required | Jenny Hill
17051 | WPAVY 17051 - The Avery Townhome - 2D Floor Plan | Create one 2D floor plan that matches the look and feel of the existing 2D floor plans. | 2013-03-05 | 2013-03-01 | 11.8 | Current | Normal | On Target | true | false | false | Approval Not Required | Jenny Hill
1301 | DZAP 1301 General | DZAP general projects / branding / miscellaneous | 2013-02-15 | 2013-02-12 | 0.7 | Current | Normal | On Target | true | true | false | Approval Not Required
2800 | New Activity Request 2800 | Through April 30, 2012 | 2012-03-19 | 2013-02-12 | 0 | Current | Normal | On Target | true | true | true | Approval Not Required
3452 | DZAP 3452 Source Requests | This project used to track source requests only. | 2013-01-14 | 2013-01-23 | 100 | Current | Normal | On Target | true | true | true | Approval Not Required
4850 | DZAP 4850 Scheduling Requests for Inactive Projects | Use this method to request scheduling or ask questions for client projects that are not currently open. May 1, 2012 | 2012-04-26 | 2012-11-21 | 0 | Current | Normal | On Target | true | true | false | Approval Not Required
4852 | New Activity Request 4852 |  | 2012-04-26 | 2012-10-02 | 100 | Current | Normal | On Target | true | true | true | Approval Not Required
4851 | EZPublish Issues 4851 | This is a project for EZPublish issues on inactive projects. | 2013-02-05 | 2013-02-12 | 91.4 | Current | Normal | On Target | true | true | true | Approval Not Required
5000 | DZAP 5000 Scheduling Requests for Inactive Projects |  | 2013-02-06 | 2013-02-11 | 93.8 | Current | Normal | In Trouble | true | true | true | Approval Not Required
6755 | MGPKP 6755 Parkland Pointe Copilot Website | as this was built in HTML, we need to schedule copilot build and QA testing. | 2012-10-26 | 2012-10-29 | 100 | Current | None | In Trouble | true | true | false | Approval Not Required
9150 | DZAP 9150 Issues for Development for Inactive Projects |  | 2012-08-02 | 2013-01-29 | 0 | Current | Normal | On Target | false | false | false | Approval Not Required
9350 | Development Project for Issues |  | 2012-12-28 | 2013-02-12 | 34 | Current | Normal | On Target | false | false | false | Approval Not Required
9551 | 9551 EZP Canceled Projects |  | 2013-02-01 | 2013-02-06 | 100 | Current | Normal | On Target | true | false | false | Approval Not Required
9752 | LL 9752 LeaseLabs themed items | Can you create a project to design the following LeaseLabs themed items: Packing Slip Shipping Label Purchase Order Either Michael or Rebecca should do this, and I need a day or 2 to describe the contents of these items. Estimated time - 3 hours. Also need some design time to create the vendor dashboard. Estimated time - 2 hours. I'd like these projects to start on Monday and be completed by Friday of next week if possible. | 2012-09-05 | 2013-02-12 | 23.9 | Current | Normal | On Target | true | true | false | Approval Not Required
10200 | Untitled Project |  | 2012-08-27 | 2013-02-12 | 0 | Current | None | On Target | true | false | false | Approval Not Required
10300 | DZAP 10300 web design project for all | It's been decided that we are going to offer clients the option to select a template design for their website. In order to do that, we need a lot of fantastic looking designs ready to go pretty quickly, which means everybody needs to pitch in. All the designs will be based on the same wireframe/structure (essentially pinestreetflats) so that development just has to build one site, and change the "skin" for the selected template. The challenge: Design at least two home page looks based on the attached wireframe (i'll also put this in the input folder once we have a job number). The fun part (thanks to Dana): 4 "winning" designs will be selected from all the submissions. The prize for each winning design is $100. You can submit as many looks as you like. And yes, it's possible for one of you to get the whole $400. I need to work with Nana to get this on the schedule, but the goal is to have designs ready by early next week. I can's stress enough how important this project is to the company--not only will it streamline our development process significantly, it will also give us a real competitive advantage against our competition. Reference: www.pinestreetflats.com | 2012-09-07 | 2013-02-08 | 60 | Current | Normal | On Target | true | false | false | Approval Not Required
11102 | WO 11102 Alta Heights and Alta Woodlake Square Items for EZP Store (!Wood Partners Folder) | WO Alta Heights and Alta Woodlake Square Items for EZP Store (!Wood Partners Folder) server file input folder: brennan prep files: toño upload to store: harrison test file: brennan | 2012-10-15 | 2013-02-12 | 21.2 | Current | Normal | In Trouble | true | true | false | Approval Not Required
11700 | sample like pinestreet |  | 2012-11-29 | 2013-04-05 | 1.2 | Current | Normal | On Target | false | false | false | Approval Not Required
11750 | sample timeline for Chris |  | 2012-11-28 | 2013-04-05 | 1.5 | Current | Normal | On Target | false | false | false | Approval Not Required
12051 | LL 12051 Create DZAP & LeaseLabs Folders | Need to create DZAP & LeaseLabs Folders that we can use to put our flyers in and give to prospects. | 2012-12-12 | 2013-01-08 | 100 | Current | Normal | In Trouble | true | true | false | Approval Not Required
12250 | LL 12250 Dev Edits to LeaseLabs.com Website | - Delete bread crumbs - Move phone number to be just below the navigation - Delete the title bar above each page's content (the bar that has the bread crumbs and the phone number in it) - How do we make the sidebar content different for each page? - Reconfigure homepage elements (see folder for edits) | 2012-11-05 | 2013-02-13 | 17.8 | Current | Normal | In Trouble | true | false | false | Approval Not Required
12251 | LL 12251 Update Bios on DZAP website | Need to update the bios on the DZAP website. See folder for edits | 2012-10-31 | 2013-02-13 | 0 | Current | Normal | In Trouble | true | true | false | Approval Not Required
12700 | LL 12700 LeaseLabs create Checklist and Control Envelope for EZPublish | This is a new item to be added to EZPublish. Please use that template. Carmel has a Checklist and Control Envelope that they own. Many past clients from them now are asking for one just like this for everyone on the store. Carmel owns the other one, so it must look slightly different. Thanks! | 2012-11-07 | 2013-01-22 | 100 | Current | Normal | In Trouble | true | true | false | Approval Not Required
14301 | LL 14301 Updates to LeaseLabs Home Page | Making minor updates to the DZAP website home page | 2012-12-17 | 2013-02-22 | 0 | Current | Normal | In Trouble | true | false | false | Approval Not Required
14654 | RRAAS 14654 Avonlea at Stonehenge EZP Setup | Please make due date for this Thursday! | 2012-12-06 | 2013-03-13 | 0 | Current | Normal | In Trouble | true | false | false | Approval Not Required
15652 | Untitled Project |  | 2013-01-03 | 2013-02-12 | 0 | Current | None | On Target | false | false | false | Approval Not Required
16650 | Untitled Project |  | 2013-02-04 | 2013-02-12 | 0 | Current | None | On Target | false | false | false | Approval Not Required
16653 | February 16653 Web2Print Social Setups |  | 2013-02-04 | 2013-02-12 | 0 | Current | None | On Target | true | false | true | Approval Not Required
17050 | Carmel Logo Font Names Requested | Carmel requested we let them know the name of all the fonts for each logo they have. This needs to be done for each property that we don't have a style guide for. Please note, this is NOT a style guide project and we should not spend the time putting together a fancy formal document. A word doc will suffice. Jenny will provide a word doc with the property list and drop all property logos into the input folder. Let's have this wrapped up by 2.15. | 2013-02-18 | 2013-02-18 | 0 | Current | Normal | On Target | true | false | false | Approval Not Required
17000 | CPWHI 9876 - Hospitality Mints |  | 2013-02-12 | 2013-02-13 | 37.5 | Current | None | On Target | true | false | false | Approval Not Required
1405 | BO 1405 Borger Corporate Responsive Website | Design and program corporate website for Borger. We have already built their property websites. NOTE: Site is Responsive | 2013-03-27 | 2013-03-14 | 54.3 | Current | Normal | On Target | true | true | true | Approval Not Required | Chris Corbin
6650 | MOVIG 6650 Village Green Copilot + Mobile |  | 2012-11-20 | 2013-02-19 | 96.9 | Current | Normal | In Trouble | true | true | false | Approval Not Required | Chris Corbin
9100 | RM 9100 Royal American Corporate Site | :: Project Scope :: ▪ Corporate website design and build. ▪ No special features or programming. ▪ Site will be launched on www.royalamerican.com ▪ Folder located at:afp://dzapsrv2._afpovertcp._tcp.local/Active/RM_9100_Royal_American_Corporate_Site | 2013-04-12 | 2013-04-17 | 65.9 | Current | Normal | At Risk | true | true | false | Approval Not Required | Chris Corbin
10501 | 10501 Park Newport Sign Design | re-opening old project 03552 | 2013-02-25 | 2013-02-22 | 14.3 | Current | Normal | At Risk | true | false | false | Approval Not Required | Chris Corbin
10702 | BRPPE 10702; Promenade Pointe - Property site Copilot | Copilot Website, mobile and IPad | 2012-12-20 | 2013-02-18 | 96.7 | Current | Normal | In Trouble | true | true | true | Approval Not Required | Chris Corbin
11003 | ATPNH 11003; Pinnacle at Nob Hill, CoPilot + Mobile + iPad+ SEO | setup copilot monthly copilot copilot mobile monthly copilot ipad setup copilot ipad monthly Approved Design Mock: http://code.l3as3labs.com/pinnacle/index.html Staging Link: http://www.leaselabs-staging.com/pinnacle-nob-hill/ Folder Location: afp://dzapsrv2._afpovertcp._tcp.local/Active/ATPNH_11003_Pinnacle_at_Nob_Hill,_CoPilot_Mobile_iPad_SEO | 2013-02-06 | 2013-02-13 | 95.2 | Current | Normal | In Trouble | true | true | true | Approval Not Required | Chris Corbin
11500 | DMJWA 11500 Jacobs Woods Apartments Copilot, Mobile & SEO | Copilot Copilot Online Application Copilot Mobile SEO Pro; 5 Search Terms | 2013-02-26 | 2013-03-06 | 82.2 | Current | Normal | At Risk | true | true | true | Approval Not Required | Chris Corbin
11504 | DMBHP 11504 The Woods at Blue Heron Pines Copilot, Online App, Mobile, SEO Pro | Copilot Copilot Mobile Copilot Online Application SEO Pro; 5 Search Terms | 2013-02-28 | 2013-03-08 | 62.2 | Current | Normal | At Risk | true | true | false | Approval Not Required | Chris Corbin
11502 | DMCAA 11502 College Arms Apartments Copilot, Online APP, Mobile, SEO | Copilot Copilot Online Application SEO Pro; 5 Search Terms | 2013-04-25 | 2013-04-25 | 8.2 | Current | Normal | On Target | true | false | false | Approval Not Required | Chris Corbin
11952 | RVCAB 11952 RV_Berkeley Central_Copilot, Mobile, Splash, SEP Pro | Copilot-Arista/Domain Mobile Splash-Alta West Davis SEO Pro- 10 search terms Staging URL: http://www.leaselabs-staging.com/berkeley | 2013-02-19 | 2013-02-26 | 86.9 | Current | Normal | At Risk | true | true | true | Approval Not Required | Chris Corbin
15052 | BOPTA 15052 Park Terrace & Crescent Apartments - Website + Mobile | Project Scope: - Currently two properties (Park Terrace & Park Crescent) are on one website. - We are to separate Park Terrace and update Park Crescent. This will include two new URL's to separate the two. - We are to use the same theme. - Includes 2 rounds of revisions to CMS site. Folder location: BOPTA_15052_Park_Terrace_Crescent_Apartments_Website_Mobile *No Dev work required for this project. | 2013-02-21 | 2013-03-08 | 6.3 | Current | Normal | At Risk | true | false | false | Approval Not Required | Chris Corbin
15062 | MX 15062 - 37 Properties - Website + Mobile + iPad +SEO Pro | ▪ 1 Wireframe ▪ 1 Theme ▪ Input scraped from websites and put in server. (Chris) ▪ SEO - 5 terms per property ▪ Mid March 2013 Launch ▪ Folder located at: afp://dzapsrv2._afpovertcp._tcp.local/Active/MX_15062_37_Properties_Website_Mobile_iPad_SEO_Pro Design Link: http://code.l3as3labs.com/maxx/index.html 1 - 300 East Seventeenth Apartments - MX300 2 - Arbour Ponds Apartment Homes - MXAPA 3 - Arcadia Villa Apartment Homes- MXAVA 4 - Ascott Pace Apartment Homes - MXASC 5 - Baker Tower Apartment Homes - MXBTA 6 - Beacon House Apartment Homes - MXBHA 7 - Boulevard @ 4201 Apartments - MXBOU 8 - Cambrian Apartment Homes - MXCAH 9 - Camelback Cove Apartment Homes - MXCCA 10 - Carriage Green Apartment Homes - MXCGA 11 - Cedar Run Apartment Homes - MXCRA 12 - Colonial Village Apartment Homes - MXCVA 13 - Concordia Apartment Homes - MXCON 14 - Deerpath on the Lake Apartment Community - MXDLA 15 - Edgewater Court Apartment Homes - MXECA 16 - Fox Ridge Apartment Homes - MXFRA 17 - Fox Valley Apartment Homes - MXFVA 18 - Glenwood Gardens Apartment Homes - MXGGA 19 - Howard Street Apartment Homes - MXHSA 20 - Lexington Court Apartment Homes - MXCLA 21 - Maple View Apartment Homes - MXMVA 22 - Meridian Garden Apartments - MXMGA 23 - Newport Mesa Apartment Homes - MXNMA 24 - Oak Ridge Apartment Homes - MXORA 25 - Palermo Apartment Homes - MXPAL 26 - Palms at Forest Hills Apartment Homes - MXPFH 27 - Parliament Apartment Homes - MXPAH 28 - Regency Court Apartment Homes - MXRCA 29 - Remington Canyon Apartment Homes - MXREM 30 - Stonybrook Apartment Homes - MXSAH 31 - The Arbors Apartment Homes - MXAAH 32 - The Cascades Luxury Apartment Community - MXCLA 33 - Ventana Canyon Apartment Homes - MXVCA 34 - Webster Lake Apartment Homes - MXWLA 35 - Wentworth Apartment Homes - MXWAH 36 - Willow Creek Apartment Homes - MXWCA 37 - Windsor Luxury Apartment Homes - MXWIN | 2013-04-02 | 2013-04-02 | 22.8 | Current | Normal | On Target | true | true | false | Approval Not Required | Chris Corbin
15100 | PIFAH 15100 - 1550 Fahrenheit - Website + Mobile | 1550 Fahrenheit Apartments 1550 East Harmon Ave. Las Vegas, NV 89119 Project Scope: - Use same wireframe as Onyx website @ http://www.theonyxapartments.com/the-onyx - Use bubble background texture. Black, white and burnt orange and chrome. The orange chrome color they like can be reviewed at: http://www.showyouraura.com/aura - 1st design mock-up to have exact look and feel of The Onyx - 2nd design mock-up can have more creative freedom - All data to be pulled from Website (Chris) - Project 6-8 weeks from 12/11/2012 Folder located at: afp://dzapsrv2._afpovertcp._tcp.local/Active/PIFAH_15100_1550_Fahrenheit_Website_Mobile Approved HP Design: http://code.l3as3labs.com/1550fahrenheit/index.html | 2013-03-05 | 2013-03-05 | 64.8 | Current | Normal | At Risk | true | true | true | Approval Not Required | Chris Corbin
15500 | MX 15500 - Corporate - Web + Mobile - ON HOLD!! | :: Project Scope :: - Basic Corporate Website - Scope to come soon - See full creative brief www.maxxrealty.com Folder located: afp://dzapsrv2._afpovertcp._tcp.local/Active/MX_15500_Corporate_Web_Mobile | 2013-02-11 | 2013-02-12 | 81.3 | Current | Normal | In Trouble | true | false | false | Approval Not Required | Chris Corbin
4450 | EZP 2 - 4450 |  | 2013-08-20 | 2013-08-07 | 47.6 | Current | Normal | On Target | true | true | true | Approval Not Required | Nana Malone
6752 | TCAST 6752 Alexan Sterling Ridge Copilot, Mobile, Floorplan Browser | alexan sterling ridge - use the alexan ribelin ranch template, with a new theme includes the mobile site and floorplan browser timeline promised to client: it's 4-6 week from design approval to go live date. So as soon as design is approved we take 4-6 to program and QA the site, set up seo / google places and launch the site live to the world. | 2015-02-27 | 2013-03-08 | 79.3 | Current | Normal | On Target | true | true | true | Approval Not Required | Erica Cohen
6753 | TCABR 6753 Alexan Briargate Copilot, Mobile, Floorplan Browser | alexan briargate - use the alexan ribelin ranch template, with a new theme includes the mobile site and floorplan browser timeline promised to client: it's 4-6 week from design approval to go live date. So as soon as design is approved we take 4-6 to program and QA the site, set up seo / google places and launch the site live to the world. | 2013-04-24 | 2013-02-28 | 65.5 | Current | Normal | At Risk | true | true | false | Approval Not Required | Erica Cohen
6754 | TCADP 6754 Alexan Deer Park Copilot, Mobile, Floorplan Browser | alexan deer park - use the alexan ribelin ranch template, with a new theme includes the mobile site and floorplan browser timeline promised to client: it's 4-6 week from design approval to go live date. So as soon as design is approved we take 4-6 to program and QA the site, set up seo / google places and launch the site live to the world. | 2015-03-20 | 2015-03-20 | 32 | Current | Normal | On Target | true | true | false | Approval Not Required | Erica Cohen
6951 | TCAOF 6951 Alexan Old Farm Copilot, Mobile, Floorplan Browser | alexan old farm - use the alexan ribelin ranch template, with a new theme includes the mobile site and floorplan browser timeline promised to client: it's 4-6 week from design approval to go live date. So as soon as design is approved we take 4-6 to program and QA the site, set up seo / google places and launch the site live to the world. | 2013-03-08 | 2013-03-04 | 86.5 | Current | Normal | On Target | true | true | false | Approval Not Required | Erica Cohen
6950 | TCAFL 6950 Alexan Fountain Lake Copilot, Mobile, Floorplan Browser | alexan fountain lake - use the alexan ribelin ranch template, with a new theme includes the mobile site and floorplan browser timeline promised to client: it's 4-6 week from design approval to go live date. So as soon as design is approved we take 4-6 to program and QA the site, set up seo / google places and launch the site live to the world. | 2015-03-10 | 2015-03-10 | 83.5 | Current | Normal | On Target | true | true | false | Approval Not Required | Erica Cohen
13600 | HGFSO 13600 HG Fenton Solterra Splash_Responsive Design_FPB_PPC_SEO_Email Marketing_3D Floorplans | - Responsive website special programming notes -Amenity hot spot map, Needs to be programmed to touch screen size resolution. -ICOVIA plug in see (srgliving.com) - interactive site plan This must also work on touch screen size, not required for iPad or mobile. (vineyards valley view functionality) Must be able to enter in pricing and availability with no feed. - Resident Portal - Splash Page - SEO (10 Keywords) - PPC - Email Marketing -3D floorplan Drawings (quantity 7) | 2013-04-01 | 2013-04-19 | 60.5 | Current | Normal | At Risk | true | true | true | Approval Not Required | Erica Cohen
14453 | TCAUC 14453 Alexan Urban Center CoPilot Website, Mobile, Floor Plan Browser, SEO | This website will use the same framework as the other Alexan sites and there will be a version for Mobile. We will also be creating a Floor Plan Browser which will be live after the live site (1/31 for live site). I spoke with Nana about this project and she suggested that Lee should be the developer assigned to this project. We are skipping the wireframe stage and moving right into layout since the client is using an existing wireframe. Note that the mock schedule that Nana did shows 1/25 as the launch date but we gave the client a schedule that shows 1/31 (just more development time. none of the design time moves). | 2013-03-27 | 2013-03-29 | 69.3 | Current | Normal | At Risk | true | true | true | Approval Not Required | Erica Cohen
16450 | AR 16450: All Properties; Pay Rent Button | Add pay rent online to each site. to place New Category under "Resident Services" on each property website that links residents to our website to pay their rent. I have attached the appropriate content to be included in the new section (Dropdown). The link in the attached content should be clickable. The title of this new section should state "Pay Rent Online". If you could place this new section above the others (e.g. community newsletter, etc.), that would be perfect. 1 Mock with 1 round of revisions for just one of the sites. Edits to be made for all sites listed below. http://www.arborproperties.com/lake-jackson/ http://www.arborproperties.com/arbor-station-fl/ http://www.arborproperties.com/arbor-trace/ http://www.arborproperties.com/arbor-view-fl/ http://www.arborproperties.com/azalea-place/ http://www.arborproperties.com/eagles-landing-pc/ http://www.arborproperties.com/eagles-landing-fl/ http://www.arborproperties.com/the-enclave/ http://www.arborproperties.com/arbor-place/ http://www.arborproperties.com/arbor-station-ms/ http://www.arborproperties.com/arbor-view-ms/ http://www.arborproperties.com/arbor-village/ | 2013-02-15 | 2013-02-15 | 0 | Current | Normal | At Risk | true | true | false | Approval Not Required | Erica Cohen
10353 | CZ 10353 Cottonwood Residential EZP Setup | CZ Cottonwood Residential EZP Setup EZP 2.0 Go Live Date 1-1-2013 Hold on set up fee billing until Jan 2013 sales order # 201874-201953 Vector logo files deliverable Anticipated Training Dates in November 2012 Go Live Date 1-1-2013 | 2012-11-19 | 2013-02-12 | 76 | Current | Normal | In Trouble | true | true | false | Approval Not Required | Amy Wickliff
11704 | FCCCT 11704 Century Citrus Towers EZPublish Setup | Group: Century-Juli Coffey Property: Century Citrus Towers email: centurycitrustowers@firstcommunities.com password: fc123 Phone: 352-394-4821 Fax: 352-394-3277 address: 1290 North Ridge Blvd. Clermont, FL 34711 Amenities: • State-of-the-Art Fitness Center • Volleyball & Tennis Court • Resort Style Pool • Tot Lot • Cyber Cafe • Lanai with Wireless Internet • Limited Access Entry • Valet Trash Monday-Friday | 2012-10-25 | 2012-10-18 | 100 | Current | Normal | On Target | true | false | false | Approval Not Required | Brennan Hartich
14262 | CX 14262 Compass Rock Real Estate EZPublish Setup (39 props) | EZP - 39 Properties to receive EZPublish Go Live Date: TBD Hold on set up fee billing for 7 days sales order # 202079-202114 Anticipated Training Dates in Mid December | 2012-12-17 | 2013-02-04 | 100 | Current | Normal | In Trouble | true | false | false | Approval Not Required | Brennan Hartich
14655 | MX 14655 Maxx Properties EZP Setup (37 Properties) | Please make the due date for this as February 10, 2013 as this will not be used until EZP2.0 is ready. | 2013-01-29 | 2013-03-15 | 0 | Current | Normal | In Trouble | true | false | false | Approval Not Required | Brennan Hartich